Online management meeting 16.06.2020

1. Situation in partner countries and schools – discussion

All schools teach online and the question of travelling is very uncertain due to the Covid situation. Also both students and teachers suffer from “screen-overdose” so we will have to wait till September with further online activities.

1. Progress of the project
2. RESULT: The Violinist – prepare for stage performance)

All schools have divided the play between the students and with the beginning of new school year we will start working on it. It is possible to introduce minimum adaptation, then we will have to choose actors and begin the rehearsals in national teams so that we are ready for the future, which may not allow to organise the assumed number of “real-life” meetings.

1. ACTIVITIES between LTT - film clubs, books, presentations, museums ect

Partners did some online activities as well as meetings at school in small groups for project activity.

1. MOBILITIES: C1 and C2 done

 C3 and C4 pending

The decision will be made in September depending on the world situation. Meanwhile we will forward and develop ideas for travelling and online meetings

1. MANAGEMENT - no problems reported
2. DISSEMINATION
* webpage
* e-Twinning
* school wall boards
* teachers / parents meetings
* leaflet / poster (Turkey)
* ideas for keeping the flow of the project: students’ diaries entry ( Covid isolation, war-like atmosphere, impressions on the films they watched or books they read during the lockdown)
1. Interim report – each country will send to coordinator the activities from their school and the coordinator will upload the description in Mobility Tool+